## Instructions
Structured individual expert judgement with ranges (using PERT formula)
Rather than a single estimate for each task, this approaches uses best case, worst case, and most likely case estimates.
The values are then combined using statistical techniques to provide both an estimate and a desired confidence interval.
Statistically, you can not simply add up the best (or worst) case scenarios and treat that as the best case.
For example, if you have 3 best case values, each of which has a 10% chance, then the chance of all three coming true is only 0.1%.
While you cannot sum up best or worst case, you can sum up the statistical variance (square of the standard deviation).
Taking the square root of the variance sum will then give you an overall standard deviation that can be used to calculate overall best/worst estimates.
Instructions
Usually you only need to enter values in the boxes styled as input:
1. Enter the project details at the top of the Estimate Workshop
2. Make sure to specify the units you are using (days, hours, weeks, etc)
3. Enter a breakdown of individual items you are estimating
4. For each item specify the best case, most likely case, and worst case estimates
5. The status column will indicate if you have not entered complete data, or if it has errors (e.g. worst is less than most likely)
Results
For planning or quoting purposes the Final estimate value, which includes Contingency, should be used.
Additional values:
The Expected value in the Estimate calculations section is the expected average time.
Note that the best/worst estimates in the calculations use the same statistical accuracy as the individual estimates.
E.g. in the realistic case you will still exceed the worst 15% of the time (1 in 6).
The result is still, however, only as good as the inputs, so the actual values should be tracked against the individual estimates;
if there is substantial deviation, then the original result will also likely be wrong.
Notes
The drop down confidence options are advanced settings and should only be changed if you understand the impact: | [5 empty] | 99.7%
The Program Evaluation and Review Technique (PERT) formula is used to calculate the expected value for each item.
However for standard deviation, the usual PERT calculation assumes the best/worst range covers 99.7% (6 standard deviations) of all values.
In practice this is unrealistic, and studies have shown that most people's sense of 90% confident is actually closer to 30% confident.
A skilled estimator should reach 70% statistical accuracy (around 2 standard deviations).
You can use a different Statistical accuracy (drop down list), but should have historical data to substantiate before doing so.
With 70% ranges, the standard deviation is calculated using a divisor of only 2.1.
This means the Estimate calculations for best/worst are also only a 70% confidence interval.
For the final estimate it is recommended to use the calculated 99.7% confidence interval, i.e. almost certain.
You can use a different confidence for the final estimate, but there is increasing chance that it will not be met.
Note that overall 99.7% confidence is what PERT aims for (it is just unrealistic to expect inputs of that level)
For more details, see "Software Estimation: Demystifying the Black Art" by Steve McConnell (although PERT estimation is applicable outside software)
Formulae Used
Notes:
Expected value (PERT) |  | = ( best + 4 * likely + worst ) / 6
Standard deviation |  | = ( worst - best ) / factor |  |  | Rather than the standard PERT factor of 6, the factor is based on the accuracy (realistic 70% factor is 2.1 std dev)
Skew |  | = ( expected - likely ) / std_dev |  |  | Pearson approximation: ( mean - mode ) / std dev, Where mean = expected and mode = likely.
Total standard deviation |  | = sqrt ( sum ( std dev ** 2 ) ) |  |  | Total std dev is calculated from sum of squares (variance).
Total skew |  | = sum ( skew * expected ) / sum ( expected ) |  |  | Total skew is weighted average (weighted by expected).
Best (total) |  | = expected - ( factor / 2 * std_dev ) + ( 2 * skew * std_dev ) |  |  | Note: Best/worst shifted right due to +ve skew; likely shifted left.
Worst (total) |  | = expected + ( factor / 2 * std_dev ) + ( 2 * skew * std_dev )
Likely (total) |  | = expected - ( skew * std_dev )
© Sly Gryphon, version 2020. This work is licensed under the Creative Commons Attribution 4.0 International License.
To view a copy of this license, visit:
https://creativecommons.org/licenses/by/4.0/
Change history
| Version | Date | Author | Notes
| 1 | 2007 | SG | Initial version.
| 2 | 2010 | SG | Updated with skew and confidence table.
| 3 | 2020 | SG | Additional instructions and formatting

## Estimate_Worksheet
Structured individual expert judgement worksheet
Client: | Customer X
Project: | Project Y
Reference:
Estimation Units: | Days
Statistical accuracy (of best/worst) | 70% (realistic) |  | 70% |  | Number of Std Dev: | 2.1
Final estimate used | 99.7% confidence (Recommended); total estimate 8.41 (Worst) |  |  |  | 11.024 | Days
|  |  | Contingency | 4.124
Estimate calculations | Best Case | Likely | Worst Case | Expected | Std Dev | Skew
| p15 | p50 | p85 | mean
| 5.701 | 6.8222 | 8.4102 | 6.9 | 1.2901 | 0.060306
Confidence table (HIDE) | % Confidence | SD Adjustment | Skew SD Adj | Total SD | Estimate | Range | Text
| 0.3% | -3 | 0.1966 | -2.8034 | 3.2833 |  | 0.3% confidence; total estimate 3.28
| 2% | -2 | 0.18781 | -1.8122 | 4.5621 |  | 2% confidence; total estimate 4.56
| 10% | -1.28 | 0.14646 | -1.1335 | 5.4376 |  | 10% confidence; total estimate 5.44
| 16% | -1 | 0.11544 | -0.88456 | 5.7588 | Best | 16% confidence; total estimate 5.76 (Best)
| 20% | -0.84 | 0.094767 | -0.74523 | 5.9386 |  | 20% confidence; total estimate 5.94
| 25% | -0.67 | 0.068921 | -0.60108 | 6.1245 |  | 25% confidence; total estimate 6.12
| 30% | -0.52 | 0.043076 | -0.47692 | 6.2847 |  | 30% confidence; total estimate 6.28
| 40% | -0.25 | -0.0086151 | -0.25862 | 6.5664 |  | 40% confidence; total estimate 6.57
| 50% | 0 | -0.060306 | -0.060306 | 6.8222 | Likely | 50% confidence; total estimate 6.82 (Likely)
| 60% | 0.25 | -0.0086151 | 0.24138 | 7.2114 |  | 60% confidence; total estimate 7.21
| 70% | 0.52 | 0.043076 | 0.56308 | 7.6264 |  | 70% confidence; total estimate 7.63
| 75% | 0.67 | 0.068921 | 0.73892 | 7.8533 |  | 75% confidence; total estimate 7.85
| 80% | 0.84 | 0.094767 | 0.93477 | 8.106 |  | 80% confidence; total estimate 8.11
| 84% | 1 | 0.11544 | 1.1154 | 8.3391 | Worst | 84% confidence; total estimate 8.34 (Worst)
| 90% | 1.28 | 0.14646 | 1.4265 | 8.7403 |  | 90% confidence; total estimate 8.74
| 98% | 2 | 0.18781 | 2.1878 | 9.7225 |  | 98% confidence; total estimate 9.72
| 99.7% | 3 | 0.1966 | 3.1966 | 11.024 |  | 99.7% confidence (Recommended); total estimate 11.02
Individual item | Best | Likely | Worst | Expected | Standard | Skew | Status
| 1 | 4 | 1 |  | Deviation
Training on timeline webpart | 0.2 | 0.3 | 0.5 | 0.31667 | 0.14286 | 0.11667 | Ok
Active Directory security group set up | 0.5 | 1 | 1.5 | 1 | 0.47619 | 0 | Ok
Branding Sales & Ops from OOTB themes | 1 | 2 | 3 | 2 | 0.95238 | 0 | Ok
Edit InfoPath form to call dummy web service | 0.5 | 1 | 1.5 | 1 | 0.47619 | 0 | Ok
Test and document process to push Sales & Ops site live | 1 | 1.5 | 2 | 1.5 | 0.47619 | 0 | Ok
Demonstrate search configuration | 1 | 1 | 1.5 | 1.0833 | 0.2381 | 0.35 | Ok
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0

## Evaluation_vs_actual
Estimate evaluation against actual
Instructions
Usually you only need to enter values in the boxes styled as input:
1. Enter the tracking start and length of tracking period.
Note that individual expert judgement is usually only appropriate for small, limited projects
2. Enter actuals by period, using the same units as the estimates.
3. You should only enter values for an individual item when it is complete.
4. The entry by period is simply to help track values and does not have to be used; only the total is relevant.
5. You don't have to complete all individual items, but can input one at a time to track project progress
Results
The sheet will calculate the Total actual, and the Magnitude of Relative Error (MRE).
It will also calculate how often your actuals are within the best/worst range, and how often they are over or under the expected
You should try and get Magnitude of Relative Error (MRE) as low as possible. This is how accurate your estimates are overall.
The Estimate Guidance evaluates where your estimates are too small or too large (whether you need to increase or decrease estimates)
The Range Guidance evaluates whether your best/worst range is too narrow or too wide (increase or decrease the range)
If your In Range percent is consistently high, you can also increase the Statistical Accuracy for future projects.
Tracking start | 2020-07-01 |  | Length (days): | 7
Calculations | Total (Days) | MRE | Under Estimated | In Range
| 3.7 | 21.94% | 33.33% | 66.67%
|  | Target | 50% | 70%
Estimates Guidance | < target P(x), increase estimates.
Range Guidance | Estimates close to target range.
Individual item | Actual | Evaluation |  |  | Actual by period (Days)
|  | MRE | Est. > Act. | In Range | 2020-07-01 | 2020-07-08 | 2020-07-15 | 2020-07-22 | 2020-07-29 | 2020-08-05 | 2020-08-12 | 2020-08-19 | 2020-08-26 | 2020-09-02 | 2020-09-09 | 2020-09-16 | 2020-09-23
Training on timeline webpart | 0.4 | 20.83% | 0 | 1 | 2020-07-01: 0.4
Active Directory security group set up | 0.8 | 25% | 1 | 0 | 2020-07-01: 0.8
Branding Sales & Ops from OOTB themes | 2.5 | 20% | 0 | 1 | 2020-07-01: 2.5
Edit InfoPath form to call dummy web service | 0
Test and document process to push Sales & Ops site live | 0
Demonstrate search configuration | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0